## Sheet1
MASTER TURNAROUND CHECKLIST
Turnaround:
Estimated Size of Turnaround in Man-hours
Planner
| Task | NAME | Target Date | Actual Date
1 | Date of S/D | OPER
2 | S/D Request Sheet Received From Operations
3 | Shutdown Duration
4 | Lead Planner |  | 1900-01-06 | 2001-01-01
5 | Responsible for Scheduling
6 | Responsible for Cost Estimate
7 | Strategic Planning Meeting |  | 1900-01-06
8 | Invite Production Planning to Strategic Planning Meeting
9 | Worklist Requested by Maintenance |  | 1900-01-06
10 | Preliminary Worklist Received From Operations
11 | Notify Enviromental Groups of Shutdown |  | 1900-01-13
12 | Special Permits, Including Area Welding, Initiated |  | 0
13 | Final Worklist Received From Operations |  | 0
14 | Determine Non-S/D Work With Operations |  | 0
15 | Shutdown Scheduled |  | 0
16 | PO Items Determined And Ordered |  | 0
17 | Establish Cut Off Date For Add-On List | MAINT | 0
18 | Completion of Cost Estimate |  | 0
19 | Send Operations C&CI Inspection Package | MAINT | 1900-01-13
20 | S/D Housekeeping Strategies Developed | MAINT | 1900-01-13
21 | Pre-S/D Information Exchange Meetings |  | 0
22 | Notification On RV's, CV's, and Process Valves |  | 0
23 | Specialty Contractors Identified and Notified of S/D |  | 0
24 | Specialty Contractors Walk-Thru Completed |  | 0
25 | Specialty Contractors Estimates Received |  | 0
26 | Specialty Contractors Job Plan Review |  | 0
27 | Vessel Mechanical Inspector Selected | MAINT | 0
28 | Exchanger Mechanical Inspector Selected | MAINT | 0
29 | All Jobs Reviewed By Maintenance Planner |  | 0
30 | Jobs tagged by planner |  | 0
31 | Manpower Requirements Established
32 | Shutdown Assistance Established for Operations
33 | Start-Up Assistance Established
34 | Equipment Requirement Identified and Dispatcher Notified
35 | Pre-S/D Supervisors Meeting
36 | Supervisor Safety Expectations Issued
37 | Site Specific Information Provided To Supervisors
38 | Supervisor Walk-Thrus
39 | Check Area Lighting
40 | All Material and Equipment Staged in Area
41 | Daily S/D Meeting Scheduled
42 | Start-Up Complete |  | 0
42 | Housekeeping Audit | MAINT | 1900-01-06
43 | S/D Critique Meeting |  | 1900-01-13
Formulas:
Target Date = [Target Date, row above]+7
Note on A9: 1. Date of S/D – The date in which an operational area plans to have a shutdown.
Note on A10: 2. S/D Request Sheet Received From Operations – The date in which the S/D Request sheet is received by Maintenance.
Note on A11: 3. Length of turnaround in days
Note on A12: 4. Lead Planner – The main planner assigned to the Shutdown.
Note on A13: 5. Responsible for Schedule Development – The Planner that will be entering and up-dating the shutdown schedule. Usually the Lead Planner.
Note on A14: 6. Responsible for Cost Estimate – The person that determines the total cost for the shutdown, based on materials, labor hours, etc… Generally the Lead Planner.
Note on A15: 7. Strategic Planning Meeting - The major shutdown scope is developed by the Site Manager, Superintendents of the Operating and Maintenance departments to decide the amount of planning needed.
Note on A17: 9. Work-List Requested by the planner – The date the planner requests the shutdown list from the maintenance or operational area.
Note on A18: 10. Preliminary Work-List Received From Operations – The date that the work-list is received.
Note on A20: 12. Special Permits, Including Area Welding, Initiated – the date in which the jobs have been reviewed for special permits & meetings scheduled (Confined Space, Area Welding, etc...).
Note on A21: 13. Final Work-List Received From Operations – the date that the final work-list is received from operations.
Note on A22: 14. Determine Non-S/D Work with Operations – the date that the shutdown list is reviewed with operations and maintenance to cull non-turnaround related work.
Note on A23: 15. All maintenance work scheduled.
Note on A24: 16. PO Items Determined And Ordered – the date that all PO’s are submitted and parts ordered for delivery
Note on A25: 17. Establish Cut Off Date for Add-On List – the date that is established with 50% of the lead time remaining for any add on jobs, so that they may be included in the cost estimate submitted with 30% of the lead time remaining. Any jobs submitted after this cut off date will not be included in the cost estimate, and will have to have a “Shutdown Add-On/Work Scope Change Request Form” filled out.
Note on A26: 18. Completion of Cost Estimate – the date the cost estimate is completed and submitted to the operational area, based on man-hours, parts, equipment, etc...
Note on A27: 19. Send Operations C&CI Inspection Package – the date that Operations receives a package from C&CI on the required Inspection of pressure vessels
Note on A28: 20.
Note on A29: 21. Pre-S/D Information Exchange Meetings – this is the date in which the planner, Operations, and Maintenance meet to exchange information about jobs that are on the shutdown list.
Note on A30: 22. Notification On RV’s, CV’s and Process Valves – the date that the vendors for relief valves, control valves and process valves are notified about when a shutdown will take place, when they can expect to receive the valves, and when they need to have back after inspection or repair.
Note on A31: 23. Specialty Contractors Identified and Notified of S/D – the date that any outside contractor is determined and notified of the shutdown, what work will be expected to take place, and what time.
Note on A32: 24. Specialty Contractors Walk-Thru Completed – the date on which any Specialty outside Contractor has been taken through and shown what Specialty Contractor Work needs to be done during a shutdown.
Note on A33: 25. Specialty Contractors Estimates Received – the date on which the Specialty Contractor submits their cost of the estimated time and equipment charges for the jobs shown to be done during a shutdown.
Note on A34: 26. Specialty Contractors Job Plan Review – the date on which the Specialty Contractor review their plans, to be done by when and when it should be completed, as well as any safety issues that need to be discussed.
Note on A35: 27. Vessel Mechanical Inspector Services Selected – the date in which a Vessel Mechanical Inspector is selected from EASTMAN Tech Staff or contractor to study and follow all Vessel Jobs during a shutdown.
Note on A36: 28. Exchanger Mechanical Inspector Selected - the date in which an Exchanger Mechanical Inspector is selected from EASTMAN Tech Staff or contractor to study and follow all Exchanger Jobs during a shutdown.
Note on A37: 29. All Jobs Reviewed By Maintenance planner – the date on which all jobs for a shutdown have been looked at and the job scope is understood, this is excluding Add-On’s or New Jobs added to final Work-list
Note on A38: 30. All Jobs Tagged By Planner – the date on which all jobs for a shutdown have been tagged for a shutdown, this is excluding Add-On’s or New Jobs added to final Work-list.
Note on A39: 31. Manpower Requirements Established – the date on which the manpower is established based on the amount of work to be done, the length of time it is to be done in, and resources are determined.
Note on A40: 32. Shutdown Assistance Established for Operations – the date on which it is established with operations what assistance, if any will be needed for the initial shutdown of an operational area.
Note on A41: 33. Start-Up Assistance Established – the date on which it is established with operations what assistance, if any will be needed for the initial start-up of an operational area.
Note on A42: 34. Equipment Requirement Identified and Scheduled – the date on which the contractor is notified of all equipment that will be required for a shutdown, including cranes, air compressors, fire suit buggy, light plants, JLG’s, cargo basket, low-boy trailer, etc...
Note on A43: 35. Pre-S/D Supervisors Meeting – the date on which the Supervisors meet with the Planners to discuss the Shutdown work to be performed.
Note on A44: 36. Supervisor Safety Expectations Issued – the date on which all of the Safety Expectations are reviewed with the Supervisors and they are reminded at the Pre-S/D meeting to have: Toolbox Safety Meetings, Job Safety Reviews, Permits and Lockout/Tagout, Proper Tools and Equipment.
Note on A45: 37. Site Specific Information Provided to Supervisors – the date on which the Supervisors are alerted to Site Specific information for the Operational Area.
Note on A46: 38. Supervisor Walk-Thrus – the date on which each supervisor is taken through the area and shown what work he/she will be responsible for.
Note on A47: 39. The Lead Planner reviews the turnaround , at night, to determine any lighting repairs or additional lighten needs if work continues around the clock.
Note on A48: 40. All Material and Equipment Staged in Area – the date on which all equipment including lock-box trailer, parts trailer, stocked with needed parts, is located in the shutdown area.
Note on A49: 41. Daily S/D Meeting Scheduled – the date in which an agreed upon daily update meeting is scheduled for the duration of the shutdown. Generally this meeting is held between 3 - 5 p.m.
Note on A50: 42. Start-Up Complete- the date on which the area actually starts up and is making production.
Note on A51: 43. Housekeeping Audit – the beginning date on which the shutdown housekeeping audits begin. Generally the first afternoon of the tunaround.
Note on A52: 43. S/D Critique Meeting – the date on which all planners and supervisors, including operations, meet to critique the shutdown.