## Action Register (hidden)
Productivity Checklist - Baton Rouge
Result Area | Productivity Goal | % Complete | Action Item | Action Item Description | Responsible Party | Due Date
Corporate Champion | Perform site Deep Dive audit | 100% | 1 | Respond with Gap Closure. Make sure one combined plan is presented for XOM and Brock. |  | 2012-02-23
Corporate Champion | Verify planning, scheduling, & framework implementation | 60% | 2 | Establish Tuesday Input meetings for T/A, North Plants and RM. XOM to provide list of contacts.
Corporate Champion | Identify & close gaps for: work processes, execution efficiencies, roles, communications, logistics, material handling, time on tools, etc. | 60% | 3 | Brock Site Leadership Team will work with XOM Department Heads to develop a list with a path forward to address these gaps in their biweekly Business meetings.
Corporate Champion | Set up site Framework Team (work group contacts) to close gaps and support their efforts | 15% | 4 | Get XOM names and establish weekly meetings (Tuesday - Thursday).
Corporate Champion |  |  | 5 | Get XOM Champion to work with Eric Chaney for driving the culture change.
Corporate Champion | Establish metrics to track progress for the sequenced schedule implementation (field audits: job starts, delays, breaks, end of day, interfaces, roadblocks, etc.) | 25% | 6 | Brock Site Leadership Team will develop a field audit form and process to collect data.
Corporate Champion | Initiate interactions between ExxonMobil and Brock site management: shape weekly meetings for comparison of frozen to actual performance, Tuesday XOM input for each work group, Wednesday Brock draft schedule and approval of Thursday frozen schedule | 50% | 7 | Get XOM participants named and set meeting schedule with Portal and demo list input provided by Brock for XOM to respond to.
Corporate Champion |  |  | 8 | Establish Wednesday review and Thursday approval steps to freeze the Brock sequenced schedule by 4:30 pm on Thursday.
Corporate Champion | Form Brock Site Leadership Team to meet with Site Business Team & XOM on alternate weeks | 50% | 9 | Schedule recuring meetings to manage this site account.
Corporate Champion |  |  | 10 | Establish the Business Meeting members and address pending issues and review the frozen vs. actual scheudle performance to shape behaviors.
Corporate Champion | Ensure roles and responsibiliteis are rolled out and enforced | 50% | 11 | Create accurate Org Chart and communicate to XOM.
Corporate Champion |  |  | 12 | Establish assigned relationships.
Corporate Champion | Initiate improvement projects and process changes to increase UR utilization and productivity | 25% | 13 | Capture list of improvement ideas and prioritize to address as part of the on going pending issues.
Corporate Champion |  |  | 14 | Keep meeting minutes and action items in the pending issues portion of the Brock Site Book.
Corporate Champion | Capture & share gains with all XOM sites | 50% | 15 | Share the feedback from this initial 2-week visit during your next Business Meeting
Corporate Champion |  |  | 16 | Add as agenda topic to Friday alignment call.
Corporate Champion | Initial team visit: 2 weeks on site | 100% | 17 | Share score and action items with site
Corporate Champion | Team off site for 1 month to allow site to impliment changes. |  | 19 | Team to maintain weekly contact and be available for consultation
Corporate Champion | 2nd team visit: 1 week on site. |  | 20 | Verify results & coach progress
Corporate Champion | Team off site for 1 month to allow for additional changes. |  | 21 | Team to maintain weekly contact and be available for consultation
Corporate Champion | 3rd team visit: 2 Days on site |  | 22 | Final evaluation and close out plans
Corporate Champion | Subsequent Team visits: 1 day |  | 23 | Team to make random Qtly observation visits

## Action Register
Action Register - Circuit Site
Action Item | Result Area | Checklist Item | Description | Responsible Party | Due Date | Update
1 | Corporate Champion | CC1 | Develop Gap Closure plan for initial assessment. Make sure plan is presented to MNT.
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113

## Corp Champion
Corporate Champion Checklist - Circuit Sites
Item # | Checklist Items for Productivity (Corporate Champion) | % Complete | Comments
CC1 | Perform site/affiliate assessment to determine present conditions
CC2 | Verify pilot work processes, MLT decision and implementation expectations are shared
CC3 | Identify and drive improvements for site/affilaite gaps (work processes, execution efficiencies, roles, communications, logistics, material handling, time on tools, interface with Central Services, etc.).
CC4 | Set up key site contacts for the Implementation Team (work group contacts) to close gaps and support their efforts
CC5 | Establish metrics to track and shape progress for the scheduled implementation improvements (field and office audits, job starts, delays, break-ins, customer interfaces, roadblocks, etc.)
CC6 | Initiate interactions between Valero and ECHO site management: shape weekly meetings
CC7 | Form ECHO Site/Affiliate Leadership Team with alternate week meeting with their team and the Customer Contact (with Valero for Maintenance)
CC8 | Ensure roles and responsibilities are rolled out and enforced for site/affiliate personnel
CC9 | Initiate and drive improvement projects and process changes to drive utilization and productivity increases
CC10 | Capture gains for sharing with all ECHO sites
CC11 | Make an initial visit (determone best length) followed by a set absence for the site/affiliate to close the identified gaps
CC12 | During the periods away from site/affilaite, the team will make weekly contacts and will always be available for questions
CC13 | Team returns for second visit to verify results and coach progress followed by another absence period
CC14 | Next make final planned visit for close out of plans
CC15 | The team will then make random one day visits each quarter
| Site Score (average percent completion of Milestones) | #DIV/0!
Circuit Site Score

## Work Process Mentor
Work Process Mentor Checklist - Circuit Site
Item # | Checklist Items for Productivity (Work Process Mentor) | % Complete | Comments
WP1 | Verify complete crew work schedule (areas, tag numbers, job packages with pictures and material needs, goal hours, specialty items, etc.) is given to each GF for distribution |  | P&S
WP2 | Witness that the GF's issue schedule and review jobs for the week with his foremen |  | P&S
WP3 | Verify communication of needed material staging for selected jobs and observe crew use of available material (best logistics, location, demo to build, etc.) |  | P&S
WP4 | Verify from field audit when the crew actually starts selected jobs |  | P&S
WP5 | Observe job start for timing to obtain permit, ease of access, safety concerns from JHA, job site preparation, support resources, etc. |  | P&S
WP6 | Verify resource allocation for each job matches needed hours for coverage |  | P&S
WP7 | Verify adequate supervision (trained and focused) for coverage to maximize productivity and ensure safe practices |  | P&S
WP8 | Verify understanding of work expectations and proper resource utilization by all levels of ECHO and Customer |  | P&S
WP9 | Coach proper execution of roles and responsibilities for all ECHO positions |  | P&S
WP10 | Ensure commitment to perform work per the schedule and estimated hour tqrgets (coach to gain buy-in and understanding) |  | P&S
WP11 | Ensure proper sizing of scaffolding for selected jobs to optimize material needs and lump sum productivity |  | P&S
WP12 | Verify that the crew understands the reasons for specific tasks on the schedule (follow job plans) |  | P&S
WP13 | Verify yard & stores quantities and locations are adequate for areas supported |  | P&S
WP14 | Ensure consumables are readily available and properly managed (cost control, enhanced productivity and safety) |  | P&S
WP15 | Ensure quality of scaffold built meets or exceeds the documented scope and user requirements (approve completed scaffold) |  | P&S
WP16 | Verify proper training, understanding and execution of required field paperwork (delays, break-ins, modifications, etc.) and compliance to ensure all billable aspects are captured correctly |  | P&S
WP17 | Verify proper scaffold tagging and job cost tracking practices are being implemented |  | P&S
WP18 | Verify timing for breaks, lunches, travel, etc. are properly managed |  | P&S
WP19 | Ensure utilization of equipment is adequate per job to control cost and enhance productivity and safety (timesheet equipment used) |  | P&S
WP20 | Verify crew feedback is given to the GF's daily for future job enhancements and to explain discrepancies |  | P&S
WP21 | Verify method of communication and approval for all break-ins |  | P&S
WP22 | Verify crew foremen communicates daily findings from actual work hours back to GF's to demonstrate crew coaching |  | P&S
WP23 | Verify materials are being staged today for tomorrow's jobs |  | P&S
WP24 | Verify crew mix (new to site, absenteeism, skill levels, etc.) to achieve estimate target costs |  | P&S
WP25 | Verify metric accuracy and definitions are being enforced |  | P&S
WP26 | Verify good working relations with customer counter parts |  | P&S
WP27 | Add items from MLT and Pilot Learnings
WP28
| Site Score (average percent completion of Milestones) | #DIV/0!
Circuit Site Score

## Management Process Facilitator
Management Process Facilitator Checklist - Circuit Site
Item # | Checklist Items for Productivity (Mgt. Process Facilitator) | % Complete | Comments
MP1 | Verify that customer work requests are being entered into their system and ours as they are initiated for all work types |  | P&S
MP2 | Verify lead time on work orders provide early start and late finish dates to identify work for 2-weeks out to be 80% accurate |  | P&S
MP3 | Review and shape process for ECHO job package development |  | P&S
MP4 | Determine who and how jobs are being walked down |  | P&S
MP5 | Audit job package content and drive improvement of needed data with pictures |  | P&S
MP6 | Evaluate Ready to Schedule backlog content and quality of work packages |  | P&S
MP7 | Verify that needed support equipment (fork lift, crane, PPE, etc.) and materials are projected in advance of start dates and make sure they are available to the crews |  | P&S
MP8 | Verify sequencing of work from the ECHO planners to be populated on the ECHO schedule |  | P&S
MP9 | Determine input from Crew Foremen and other field personnel for sequencing and optimum performance |  | P&S
MP10 | Establish ECHO weekly meeting for review of previous week's schedule for ECHO churn and why, work to carry over, sequencing improvements needed, and work for upcoming week (Project Manager, superintendent, schedulers, planners and GF's) |  | P&S
MP11 | Identify jobs to be walked down by the GF's with the crew foreman to get ready for execution |  | P&S
MP12 | Verify that the scheduler incorporates feedback from the field walks before sharing draft schedule with Customer |  | P&S
MP13 | Verify customer point of contact for each work type receives the draft schedule and provides input for any needed changes before finalizing |  | P&S
MP14 | Based on updated customer input, finalize material needs and job bundling, the schedule is set |  | P&S
MP15 | Verify the distribution of the schedule and job packages to the foremen and crew level with questions resolved |  | P&S
MP16 | Verify that the GF's are providing estimated work hours for each job to the crews daily |  | P&S
MP17 | Review daily crew feedback on actual job productivity (timesheets and schedule feedback: earn vs. burn) |  | P&S
MP18 | Verify weekly job progressions (actual vs. estimated quantities) for each job each week |  | P&S
MP19 | Compare estimated data to actual spent man hours to finalize productivity |  | P&S
MP20 | Verify field coaching is occurring daily to identify areas of concern |  | P&S
MP21 | Verify metric accuracy and definitions are being enforced |  | P&S
MP22 | Verify good working relations with customer counterparts |  | P&S
MP23 | Add items from MLT and Pilot Learnings
MP24
| Site Score (average percent completion of Milestones) | #DIV/0!
Circuit Site Score

## Site Overall Score
Average % Completion of Milestones | 2017-04-17 | 2017-05-08 | 2017-05-29
Corporate Champion | 0 | 0 | 0 | 0
Work Process Mentor | 0 | 0 | 0 | 0
Management Process Facilitator | 0 | 0 | 0 | 0
Site Score | 0 | 0 | 0 | 0
Circuit Site - Motiva
Average % Completion of Milestones | 2017-04-24 | 2017-05-15 | 2017-06-05
Corporate Champion | 0 | 0 | 0 | 0
Work Process Mentor | 0 | 0 | 0 | 0
Management Process Facilitator | 0 | 0 | 0 | 0
Site Score | 0 | 0 | 0 | 0
Circuit Site - Total
Average % Completion of Milestones | 2017-05-01 | 2017-05-22 | 2017-06-12
Corporate Champion | 0 | 0 | 0 | 0
Work Process Mentor | 0 | 0 | 0 | 0
Management Process Facilitator | 0 | 0 | 0 | 0
Site Score | 0 | 0 | 0 | 0
Circuit Site - Exxon

## Visit Schedule
Week Of (Monday) | Site to Visit
2017-04-17 | Motiva
2017-04-24 | Total
2017-05-01 | Exxon
2017-05-08 | Motiva
2017-05-15 | Total
2017-05-22 | Exxon
2017-05-29 | Motiva
2017-06-05 | Total
2017-06-12 | Exxon
2017-06-19 | Evaluate for other sites
2017-06-26
2017-07-03
2017-07-10
2017-07-17
2017-07-24
2017-07-31
2017-08-07
2017-08-14
2017-08-21
2017-08-28
Site visit pattern will be a 1-week initial visit followed by a 2-week absence.
The second visit is for 1-week with another 2-week absence followed by a
2-day visit for final verification of results.

## General Action Items
Productivity Implementation Checklist - Circuit Site
General Action Items for Valero: (in addition to the Milestones)
1. Seek to understand before taking actions (eliminate knee jerk reactions)